## AWP 2017
Area | Goal or Objective | High Level Activity | Means of Verification | Funded /Unfunded | Funding Priority level | Responsible Organisation for Funding the Activity | Activity Cost UGX | Activity Cost $ | Time Frame | UNEPI Lead Persons | Stakeholder Focal Point | Comment | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Q1 | Q2 | Q3 | Q4
Program management & Financing | To set a sustainable immunization funding mechanisim | Support setting up of the immunisation fund and the implementation as provided in the immunisation act 2016 | SOPs | Funded | High | UNICEF/PATH | 0 | 13985 | JAN-DEC | UNEPI PM | Eva/Brian | [13 empty] | 1 | 1 | 1 | 1
Program management & Financing | Increase knowledge of available funding (budget) so as to increase performance | Establish mechanism for tracking and reporting immunisation fund and expenditure | Quarterly reports | Funded | High | WHO | 0 | 8998 | JAN-DEC | Nghania | Annet | Conduct monthly | [12 empty] | 1 | 1 | 1 | 1
Program management & Financing | Increase knowledge of available funding (budget) so as to increase performance | Integrate financial tracking system within UNEPI dashboard | Access to operating dash board by stakeholders | Funded | High | CHAI | Staff TA | Staff TA | MAY-DEC | Banura | Lorraine | Regular up grade to be done yearly | [12 empty] | 0 | 1 | 1 | 1
Program management & Financing | Increase knowledge of available funding (budget) so as to increase performance | Integrate financial tracking system within UNEPI dashboard | Access to operating dash board by stakeholders | Funded | High | CHAI | Staff TA | Staff TA | MAY-DEC | Banura | Lorraine | Regular up grade to be done yearly | [12 empty] | 0 | 1 | 1 | 1
Program management & Financing | Provide strategic direction, oversight, transparency, planning and ownership to UNEPI | Support the establishement of ICC (development of TORs, Orientation of members, review of performance indicators | TOR and committee established | Funded | High | CHAI/WHO | 0 | 2000 | FEB-JUNE | Banura | Lorraine | CHAI supports UNEPI in | [12 empty] | 1 | 1 | 0 | 0
Program management & Financing | Provide strategic direction, oversight, transparency, planning and ownership to UNEPI | Conduct regular meetings of the ICC | Minutes | Funded | High | UNEPI/WHO | 0 |  | JUNE -DEC | Banura | Annet | [13 empty] | 0 | 0 | 1 | 1
Program management & Financing | Provide strategic direction, oversight, transparency, planning and ownership to UNEPI | Review program performance through UNEPI dashboard | Shared Analysis | Funded | High | UNEPI/CHAI | Staff TA | Staff TA | FEB-DEC | PM UNEPI | Lorraine | Dashboards will be used to create distric performance reports | [12 empty] | 1 | 1 | 1 | 1
Program management & Financing | Introduce new and under utilized vaccines into the programme | Proposal writing for MR application | Final proposal application |  | High | UNEPI/WHO | 0 |  | Feb - May | Banura/Ampeire | Annet | [13 empty] | 1 | 1 | 0 | 0
Program management & Financing | Introduce new and under utilized vaccines into the programme | Support the identification and mitigation of barriers to HPV2 uptake | Report | Funded | High | CHAI | 0 | 10000 | FEB-DEC | UNEPI PM | Lorraine | [13 empty] | 1 | 1 | 1 | 1
Program management & Financing | Increase funds available to UNEPI for Immunisation System Strengthening | Development of HSSP II workplan and SOPs | HSSPII work plan |  | High | UNEPI/GAVI | 0 |  | FEB-MAY | Banura / Nghania | All HDPs | [13 empty] | 1 | 1 | 0 | 0
Program management & Financing | To ensure the district have EPI centered activities that can be implemented by the district EPI focal person | Support districts in development of Annual workplan, and RED/REC Micro-plans and ensure their implementation | Evidence of Microplans | Funded | High | WHO/CHAI | 0 | 167045 | JAN-JUNE | PM UNEPI/UNEPI-DPM/Nghania | Annet/Lorraine | [13 empty] | 1 | 1 | 0 | 0
Program management & Financing | Provide strategic direction, oversight, transparency, planning and accountability to UNEPI | Evaluate Quarterly UNEPI RI performance | Quarterly Analysis report |  | High | CHAI/WHO/PATH | 0 | 7490 | MAR, JUNE, SEP, DEC | UNEPI PM /Frehd | All HDPs | [13 empty] | 1 | 1 | 1 | 1
Program management & Financing | Evaluate Annually UNEPI performance | Support development of 2016 JAR | JAR report | Funded | High | WHO | 0 | 7490 | JAN-JUNE | PM UNEPI/Tabley | Annet | [13 empty] | 0 | 0 | 0 | 1
Program management & Financing | Improve tracking and review of regional and district level performance | Print and disseminate EPI policy | Printed Policy | Funded | Medium | MCSP | 0 | 8000 | MAY-JUNE | UNEPI PM | Gerald | [13 empty] | 0 | 1 | 0 | 0
Program management & Financing | To improve vaccine uptate | Conduct pilot project in Bukedea to improve vaccine uptake | Report | Funded | Medium | GSK | 0 | 10000 | MAY-JUNE | UNEPI PM | Molly | Awaiting paper work submission to funder | [12 empty] | 0 | 1 | 0 | 0
Program management & Financing | Improve tracking and review of regional and district level performance | Support capacity building of immunisation at district level through regional supervisor mentorships | Report | Funded | High | CHAI | 0 | 30000 | FEB- JUNE | UNEPI PM | Lorraine | Already ongoing | [12 empty] | 1 | 1 | 0 | 0
Program management & Financing | Provide strategic planning and review of UNEPI performance | Conduct Monthly EPI technical meetings | Minutes | Funded | High | UNEPI/PATH/CHAI/WHO/UNICEF/MCSP-SS4RI | 0 | 500 | JAN_DEC | UNEPI PM | All HDPs | Alternating hosting | [12 empty] | 1 | 1 | 1 | 1
Program management & Financing | Strengthen district and Health Facility Level vaccine management practices | Conduct monthly feedback to districts on RI and Performance | Reports |  | High | UNEPI | 0 |  | JAN-DEC | UNEPI-PM/UNEPI-DPM | All HDPs | [13 empty] | 1 | 1 | 1 | 1
Program management & Financing | Provide strategic planning and review of UNEPI performance | Conduct Quarterly UNEPI work plan review | Reviewed work plan performance |  | High | UNEPI/UNICEF/PATH/CHAI | 0 | 18490 | APRl, JUL, OCT, DEC | UNEPI PM/Banura/Nghania | All HDPs | Alternating hosting | [12 empty] | 1 | 1 | 1 | 1
Program management & Financing | Provide strategic planning and review of UNEPI performance | Conduct Annual UNEPI work plan review and develop AWP for the new year | Reviewed 2017 work plan, 2018 Annual work plan developed |  | High | UNEPI/UNICEF/PATH/CHAI | 0 | 12875.5 | DEC | UNEPI PM/Banura/Nghania | All HDPs | Alternating hosting | [12 empty] | 0 | 0 | 0 | 1
Program management & Financing | Strengthen national-level management of district immunization program performance | Conduct district performance review meetings in 7 focus districts | Quarterly review meetings |  | High | CHAI/MOH | 0 | 40000 | MAY-DEC | Patrick | Jalia/Matthew | [13 empty] | 0 | 0 | 1 | 1
Program management & Financing | Strengthen routine VPD surveillance laboratory practicies | Support functionality of national polio committees (NCC, NPEC, NTF) | Minutes | Funded | High | WHO | 0 | 41374 | JAN-DEC | PM UNEPI | Annet | [13 empty] | 1 | 1 | 1 | 1
Program management & New Vaccine introduction | Ensure timely and efficient introduction of new vaccines | Develop Rotavirus Vaccine training guidelines and Social mobilisation tools | Guideline and tools | Funded | High | WHO/UNICEF/ GSK/UNEPI | 0 | 20000 | FEB | UNEPI-PM | All HDPs | [13 empty] | 1 | 0 | 0 | 0
Program management & New Vaccine introduction | Ensure timely and efficient introduction of new vaccines | Conduct trainings for Rotavirus Vaccine | Training plan | Funded | High | WHO/UNICEF/ GSK/UNEPI | 0 | 50000 | FEB | UNEPI-DPM/Banura | All HDPs | [13 empty] | 0 | 1 | 0 | 0
Program management & New Vaccine introduction | Ensure timely and efficient introduction of new vaccines | Track progress of implementation of Rotavirus Vaccine microplan (communication and disbursemsents to districts, tracking stock status, conducting launch preparation meetings,etc) | Implementation plan | Funded | High | CHAI/UNEPI/GSK/WHO | Staff TA | Staff TA | FEB | Banura | Annet/Lorraine | [13 empty] | 1 | 1 | 0 | 0
Program management & New Vaccine introduction | Ensure timely and efficient introduction of new vaccines | Introduce RV1 nationwide | UDHS Monthly Rota vaccination reports | Funded | High | UNEPI/WHO/UNICEF/CHAI/MCSP/PATH/GSK | 0 | 25000 | MAY | UNEPI-PM | All HDPs | [13 empty] | 0 | 1 | 0 | 0
Program management & New Vaccine introduction | Ensure timely and efficient introduction of new vaccines | Conduct Rotavirus Vaccine PIE | PIE report | Funded | High | WHO | 0 |  | FEB-DEC | UNEPI-DPM/Banura | Annet | [13 empty] | 0 | 0 | 0 | 1
Program management & New Vaccine introduction | Support NVI proposal development | Support for NVI proposals (proposal development depending on UNITAG advise and MR, PIE HPV, Td, IPV, HepB birth dose) | UNITAG report and Proposal applications | Funded | High | WHO/CHAI/PATH | 0 | 141347 | JAN-DEC | Ampeire/Banura | All HDPs | [13 empty] | 1 | 1 | 1 | 1
Program management & New Vaccine introduction | Increased visibility and prioritization of financing requirements for RI service delivery | Support functionality of UNITAG roles | Meeting Minutes and shared | Funded | High | WHO | 0 | 10700 | JAN-DEC | Ampeire | Annet | [13 empty] | 1 | 1 | 1 | 1
Advocacy, Communication & Social Mobilization | To Solicit support of the religious leaders in mobilizing their communities for Immunization services | Regional orientation meetings with religious leaders on RI and NVI | Reports of meeting and Specifics of Religious leaders |  | Medium | UNEPI/UNICEF | 0 | 30000 | MAR | Tabley | Eva | These will be conducted in 10 Health regions | [12 empty] | 1 | 0 | 0 | 0
Advocacy, Communication & Social Mobilization | To Hold EPI advocacy meetings wth the top cultural leaders | National orientation meeting for cultural leaders | Report and signed renewed Resolutions by the leaders |  | Medium | UNEPI/UNICEF | 0 | 20000 | MAR | Tabley | Eva | To be attended by King and Chiefdom leaders | [12 empty] | 1 | 0 | 0 | 0
Advocacy, Communication & Social Mobilization | Strengthen integration of RI mobilization with Health and other social services and activities | Orientation meeting with extension workers at district level on RI | Reports of orientation meetings conducted and Number extension workers oriented on RI |  | High | UNEPI/UNICEF | 0 | 20000 | JUN, JUL | Tabley | Eva | These will be conducted in all districts | [12 empty] | 0 | 1 | 1 | 0
Advocacy, Communication & Social Mobilization | To solicit support of the political leaders for EPI advocacy and social mobilization | Orientation meeting with district councils on EPI | Reports and Action plans developed by the district councilors |  | Medium | UNEPI/UNICEF | 0 | 20000 | JUN, JUL 2017 | Tabley | Eva | These will be conducted in all districts | [12 empty] | 0 | 1 | 1 | 0
Advocacy, Communication & Social Mobilization | To carry outintensive grass root mobilization in 40 poorly performing districts | Intesive social mobilisation using film vans in 40 poorly perfoming districts | Number of districts reached and reports of sessions conducted |  | High | UNEPI/UNICEF | 0 |  | APR, OCT | Tabley | Eva | To conducted in 40 poorly perfoming districts | [12 empty] | 0 | 1 | 0 | 1
Advocacy, Communication & Social Mobilization | To run an EPI media campaign on National, Regional and Local Radio and TV stations | a) Develop Radio and TV messages on NVI and RI b) Radio and TV messages nation wide | Message package and Evidence of Radio and TV messages | Funded | High | UNEPI/UNICEF | 0 | 82042 | APR | Tabley | Eva | This to run for one Month every querter | [12 empty] | 0 | 1 | 0 | 1
Advocacy, Communication & Social Mobilization | Increase advocy for routine immunization | Conduct 6th African vaccination week (AVW). | Activity report |  | High | WHO/UNICEF/CHAI/MCSP/CDC | 0 | 30000 | APR | Tabley | All HDPs | This to conducted last week of April 2017 | [12 empty] | 0 | 1 | 0 | 0
Advocacy, Communication & Social Mobilization | Increase community awareness and demand for routine immunization services | Sensitize VHTs on new vaccines , including refresher training on RI | Reports and Number of VHTs reached |  | Medium | UNEPI/UNICEF | 0 | 30000 | APR, MAY, JUN | Tabley | Eva | VHTs will also be oriented on NVI | [12 empty] | 0 | 1 | 0 | 0
Advocacy, Communication & Social Mobilization | Increase community awareness and demand for routine immunization services | Conduct advocacy meetings with parliamentarians | Activity report |  | High | UNEPI/UNICEF | 0 | 20000 | APR | Tabley | Eva | [13 empty] | 0 | 1 | 0 | 0
Advocacy, Communication & Social Mobilization | To reviw Routine Immunization performance, analysise engagment of mobilization partners, acheivements and outcome | Conduct quarterly Advocay, communication and social mobilisation meetings with partners | Report and Minutes of the quarterly meetings |  | High | UNEPI/UNICEF | 0 | 10000 | MAR, JUN, SEPT, DEC | Tabley | Eva | The quartely meetings will be attended by ACSM partners | [12 empty] | 1 | 1 | 1 | 1
Monitoring, Supervision & Evaluation | Improve quality and usage of data by UNEPI for decision making | Support data quality regional review meetings focusing on high risk regions with gaps in data quality | Report and Minutes | Funded | High | CDC | 0 | 16413.7785 | JUN-NOV | Ampeire | Kevin Mugenyi | Brought forward from 2016 | [12 empty] | 0 | 1 | 1 | 1
Monitoring, Supervision & Evaluation | Improve quality and usage of data by UNEPI for decision making | Finalizing DIT year 2 Project implementation strategy | Report |  | High | CDC-AFENET | 0 |  | FEB | Ampeire | Kevin Mugenyi | Completed; Planning Committee minutes shared with stakeholders | [12 empty] | 1 | 0 | 0 | 0
Monitoring, Supervision & Evaluation | Improve quality and usage of data by UNEPI for decision making | Review and adjust DIT M&E tools as required | Finalised and Printed Tools | Funded | High | CDC-AFENET | 0 |  | FEB | Ampeire | Kevin Mugenyi | Completed, tools updated with stakeholders' inputs. Review conducted during training curriculum review meeting in row below | [12 empty] | 1 | 0 | 0 | 0
Monitoring, Supervision & Evaluation | Improve quality and usage of data by UNEPI for decision making | Review and adjust training curriculum for DITs as required | Training Plan | Funded | High | CDC-AFENET | 0 | 384 | FEB | Ampeire/Ampeire | Kevin Mugenyi | On track for completion by end February 2017. Meeting merged with M&E tool review above | [12 empty] | 1 | 0 | 0 | 0
Monitoring, Supervision & Evaluation | Improve quality and usage of data by UNEPI for decision making | DIT Regional-level targeted trainings | Training Plan | Funded | High | CDC-AFENET | 0 |  | Mar-Dec 2017 | Ampeire/UNEPI-DPM | Kevin Mugenyi | [13 empty] | 1 | 1 | 1 | 1
Monitoring, Supervision & Evaluation | Improve quality and usage of data by UNEPI for decision making | DIT field deployment/on-job mentorship at district and health-facility level, and implementation of Data Quality Intervention Tool, and other M&E tools, at district level, and on-job mentorship of health workers at health facility level | Mentorship Plan and Reports | Funded | High | CDC-AFENET | 0 | 65023.9504 | Mar-Dec 2017 | Ampeire/UNEPI-DPM | Kevin Mugenyi | [13 empty] | 1 | 1 | 1 | 1
Monitoring, Supervision & Evaluation | Improve quality and usage of data by UNEPI for decision making | Collection of DIT M&E data and compiling/submitting deployment reports | Reports | Funded | High | CDC-AFENET | 0 |  | MAR-DEC | Ampeire/Nghania | Kevin Mugenyi | [13 empty] | 1 | 1 | 1 | 1
Monitoring, Supervision & Evaluation | Improve quality and usage of data by UNEPI for decision making | Attend a DIT regional-level meeting in the quarter following deployment to provide feedback on and discuss deployment activities, outputs and areas for improvement | Minutes | Funded | High | CDC-AFENET | 0 | 16413.7785 | MAR-DEC | Ampeire/Nghania | Kevin Mugenyi | [13 empty] | 1 | 1 | 1 | 1
Monitoring, Supervision & Evaluation | Improve quality and usage of data by UNEPI for decision making | National Support Supervision of DITs, including monitoring activities at the district and health facility level during DIT deployment | Reports | Funded | High | CDC-AFENET | 0 | 16193.2134 | MAR-DEC | Ampeire/UNEPI-DPM | Kevin Mugenyi | [13 empty] | 1 | 1 | 1 | 1
Monitoring, Supervision & Evaluation | Improve quality and usage of data by UNEPI for decision making | Participate in mid-term DIT project review meeting | Reports | Funded | High | CDC-AFENET | 0 | 5444 | NOV | Ampeire/Nghania | Kevin Mugenyi | [13 empty] | 0 | 0 | 0 | 1
Monitoring, Supervision & Evaluation | Improve quality and usage of data by UNEPI for decision making | Conduct external monitoring and evaluation activity to document progress and impact of DITs | Reports | Funded | High | CDC-AFENET | 0 |  | MAR, JUN, SEPT, DEC | Ampeire/Nghania | Kevin Mugenyi | [13 empty] | 1 | 1 | 1 | 1
Service Delivery & Training | Strengthen district and Health Facility Level routine immunisation practices | Printing of the IIP manual | Finalised and Printed IIP | Funded | High | MCSP-SS4RI/WHO/UNICEF/CHAI/PATH | 0 | 5500 | APR | UNEPI-DPM | Gerald/Possy | [13 empty] | 0 | 1 | 0 | 0
Service Delivery & Training | Strengthen district and Health Facility Level routine immunisation practices | Develop IIP training materials (PPT) | Finalised training materials | Funded | High | UNEPI | 0 | 1000 | MAR, APR | Mutonyi | All HDPs | [13 empty] | 0 | 1 | 0 | 0
Service Delivery & Training | Strengthen district and Health Facility Level routine immunisation practices | Conduct mentorship for health workers in the 3 Newly constructed hospitals of KCCA 1.Kiruddu Hospital 2. Kawempe Hospital and 3. Naguru including the entire health facilities of KCCA | Reports |  | High | UNEPI/WHO/CDC | 0 |  | MAR, APR, MAY, JUN | Mutonyi / Ampeire | Annet/Patricia | Intergrate with surveillance | [12 empty] | 0 | 1 | 0 | 0
Service Delivery & Training | Strengthen district and Health Facility Level routine immunisation practices | Conduct National Training of Trainers in IIP | Reports |  | High | WHO/UNICEF/CHAI | 0 |  | MAR | Mutonyi | All HDPs | [13 empty] | 1 | 0 | 0 | 0
Service Delivery & Training | Strengthen district and Health Facility Level routine immunisation practices | Conduct Training of Tutors in IIP in 100 institutions | Reports |  | High | MCSP-SS4RI/WHO/UNICEF | 0 | . | APR | Mutonyi | All HDPs | [13 empty] | 0 | 1 | 0 | 0
Service Delivery & Training | Strengthen district and Health Facility Level routine immunisation practices | Conduct OPL training to 50 Districts health workers | Reports | Funded | High | WHO/UNICEF/CHAI/MCSP | 0 | 60300 | MAY-DEC | Mutonyi | All HDPs | [13 empty] | 0 | 1 | 1 | 1
Service Delivery & Training | Strengthen district and Health Facility Level routine immunisation practices | Conduct MLM training of UNEPI and District leaders | Reports |  | Medium | WHO/UNICEF/MCSP | 0 |  | JUN-AUG | Mutonyi | Annet/Eva/Gerald | [13 empty] | 0 | 1 | 1 | 0
Service Delivery & Training | Strengthen district and Health Facility Level routine immunisation practices | Print and disseminate RI Job Aids (Flip Charts) | Finalised and Printed Flip Chart |  | High | WHO/UNICEF/CHAI | 0 |  | APR, MAY, JUN, JUL | Mutonyi /Bakkabulindi | Annet/Eva/Lorraine | [13 empty] | 0 | 1 | 1 | 0
Service Delivery & Training | Strengthen district and Health Facility Level routine immunisation practices | Printing of training institution's curriculum | Finalised and Printed Curriculum |  | High | MoH/WHO/UNICEF/CDC-AFENET/PATH/CHAI/MCSP-SS4RI | 0 |  | MAR | Mutonyi | All HDPs | [13 empty] | 1 | 0 | 0 | 0
Service Delivery & Training | Implement the recommendations of TNA | Provide updated training materials for training institutions | Printed Materials |  | High | MoH/WHO/UNICEF/CDC-AFENET/PATH/CHAI/MCSP | 0 |  | JUN | Mutonyi | All HDPs | [13 empty] | 0 | 1 | 0 | 0
Service Delivery & Training | Strengthen district and Health Facility Level vaccine management practices | Conduct Quarterly Feedback to districts (newspaper pull out) | Printed News paper pull out | Funded | High | MCSP | 0 | 26241 | MAR, JUN, SEPT, DEC | Ampeire | Gerald/Possy | [13 empty] | 1 | 1 | 1 | 1
Service Delivery & Training | Strengthen district and Health Facility Level vaccine management practices | Update National RED/REC guidelines | Finalised and Printed Guidelines |  | High | WHO/UNEPI | 0 |  | JUN, JUL | Banura | Annet | [13 empty] | 0 | 1 | 1 | 0
Service Delivery & Training | Strengthen district and Health Facility Level vaccine management practices | Disseminate National RED/REC guidelines | Finalised and Printed Guidelines |  | High | WHO/UNEPI | 0 |  | JUL | UNEPI-PM | Annet | [13 empty] | 0 | 0 | 1 | 0
Service Delivery & Training | Strengthen district and Health Facility Level vaccine management practices | Support health facilities to implement the RED/REC microplans | Microplans |  | High | MoH/WHO/UNICEF/CDC-AFENET/PATH/CHAI/MCSP-SS4RI | 0 |  | JUL, AUG | UNEPI-DPM | All HDPs | [13 empty] | 0 | 0 | 1 | 1
Service Delivery & Training | Strengthen district and Health Facility Level vaccine management practices | Conduct RI support supervision/mentorship in 40% low performing districts | Report |  | High | UNEPI/WHO/CHAI/UNICEF/MCSP | 0 |  | JUL | Mutonyi/Luzze | All HDPs | [13 empty] | 0 | 0 | 1 | 0
Service Delivery & Training | Strengthen district and Health Facility Level vaccine management practices | Conduct focused supportive supervison in 7 new districts | Supervision Plan and Report |  | High | MoH/WHO/UNICEF/CDC-AFENET/PATH/CHAI/MCSP-SS4RI | 0 |  | JUL, AUG | Mutonyi/Luzze | All HDPs | [13 empty] | 0 | 0 | 1 | 0
Service Delivery & Training | Strengthen district and Health Facility Level vaccine management practices | Finalisation of EPI Immunisation standards | Finalised EPI Immunisation Standards | Funded | High | SS4RI | 0 | 3800 | APR | Banura | Gerald/Possy | [13 empty] | 0 | 1 | 0 | 0
Service Delivery & Training | Strengthen district and Health Facility Level vaccine management practices | Print and disseminate EPI Immunisation Standards | Printed Immunisation Standards |  | Medium | WHO/AFENET/MCSP-SS4RI | 0 |  | MAY, JUN | UNEPI-PM | All HDPs | [13 empty] | 0 | 1 | 0 | 0
Service Delivery & Training | Strengthen district and Health Facility Level vaccine management practices | HS Operational research case study of Hoima district | Results disseminated | Funded | Medium | WHO | 0 | 50000 | MAY, JUN, JUL | UNEPI-PM/UNEPI-DPM | Annet | [13 empty] | 0 | 1 | 1 | 0
Service Delivery & Training | Strengthen district and Facility levele cold chain and vaccine management practices | Orient Health workers on immunization waste disposal in collaboration with Environmental Health Division -service delivery |  |  | Medium | UNEPI | 0 |  |  | Mutonyi |  | No funding required | [12 empty] | 0 | 1 | 1 | 1
Data Quality improvement | Improve quality and usage of data by UNEPI for decision making | Indepth assesment of EPI information management system | Proposal and Report | Funded | High | WHO | 0 | 16050 | MAR, APR, MAY, JUN | UNEPI-DPM/Ampeire | Annet | TO GET CONSULTANT TO UNDERTAKE THIS ACTIVITY | [12 empty] | 1 | 1 | 0 | 0
Data Quality improvement | Improve quality and usage of data by UNEPI for decision making | Develp National EPI Multi Year Data Quality Improvement Plan | Proposal and Plan | Funded | High | WHO | 0 | 10700 | MAR, APR, MAY, JUN | UNEPI-DPM/Ampeire | Annet | JOINT ACTIVITY FOR PARTNERS | [12 empty] | 1 | 1 | 0 | 0
Data Quality improvement | Improve quality and usage of data by UNEPI for decision making | Support the implementation and monitoring of the DQIP in collaboration with other partners” | Report | Funded | High | WHO/CDC | 0 | 30000 | JAN-DEC | UNEPI-DPM/Ampeire | Annet/Patricia | JOINT ACTIVITY FOR PARTNERS | [12 empty] | 1 | 1 | 1 | 1
Data Quality improvement | Improve quality and usage of data by UNEPI for decision making | Conduct data quality mentorship at health facility in a total district 50 districts in close collaboration with CDC | Report |  | High | WHO/CDC | 0 |  | JAN-DEC | UNEPI-DPM/Ampeire | Annet/Patricia | WHO/CDC, CDC HAS FUNDS | [12 empty] | 1 | 1 | 1 | 1
Service Delivery & Training | Strengthen district and Health Facility Level vaccine management practices | Institutionalise implementation of Equity and coverage recommendations through RED/REC | Report | Funded | High | WHO/UNICEF | 0 | 80000 | JAN-DEC | UNEPI-PM/UNEPI-DPM | Annet/Eva | [13 empty] | 1 | 1 | 1 | 1
Service Delivery & Training | Strengthen district and Health Facility Level vaccine management practices | Support the implementation of Coverage and Equity recommendations through RED/REC strategy in 40 selected districts | Report | Funded | High | WHO | 0 | 23972 | JAN-DEC | UNEPI-PM/UNEPI-DPM | Annet | [13 empty] | 1 | 1 | 1 | 1
Vaccine, Logistics, Equipments and Infrastructure | Strengthen district and Facility levele cold chain and vaccine management practices | Review job aids, fridge tag guidelines,EPI support supervision check list and Score card to include new areas of Cold chain management & basic preventive maintenance plan; review temperature monitoring charts (daily & monthly) and print | Reviewd materials and workshop Report | Funded | High | UNICEF/PATH | 0 | 67500 | FEB, MAR | Lubwama/Lanyero | Eva/Brian | Printing to be done by end March 2017 | [12 empty] | 1 | 0 | 0 | 0
Vaccine, Logistics, Equipments and Infrastructure | Strengthen district and Facility levele cold chain and vaccine management practices | Conduct a review of the fridge tag roll out activities | Review plan/Report | Funded | High | UNICEF | 0 | 28606 | FEB, MAR | Lubwama/Gilbert | Eva | Review plan/report | [12 empty] | 1 | 0 | 0 | 0
Vaccine, Logistics, Equipments and Infrastructure | Strengthen district and Facility levele cold chain and vaccine management practices | Conduct training of DCCT/DCCA for all 116 districts on CC, vaccine management and basic preventive maintanance of CCE | Training plan/Report | Funded | High | UNICEF | 0 | 93280 | FEB, MAR | Pamela Zaninka/Humphrey | Eva | Provide concept (Pamela/Humphrey/Gilbert) | [12 empty] | 1 | 0 | 0 | 0
Vaccine, Logistics, Equipments and Infrastructure | Strengthen district and Facility levele cold chain and vaccine management practices | Distribute CCE maintainace kits | Distribution plan and Report |  | High | NMS | 0 |  | MAR, APR | Gilbert/Musubire |  | Distribution plan/integrate with routine logistics distribution | [12 empty] | 1 | 1 | 0 | 0
Vaccine, Logistics, Equipments and Infrastructure | Strengthen district and Facility levele cold chain and vaccine management practices | Distribute Job aides, fridge tag guidelines, daily temperature monitoring charts & Monthly Temperature Reporting forms)(booklets) to all health facilities | Distribution plan and Report |  | High | NMS | 0 |  | MAR, APR | William Musubire |  | Distribution plan/integrate with routine logistics distribution | [12 empty] | 1 | 1 | 0 | 0
Vaccine, Logistics, Equipments and Infrastructure | Strengthen district and Facility levele cold chain and vaccine management practices | Monitoring implimentation of district level preventive maintenance plans in all 116 districts | Supervision plan/Report | Funded | Medium | UNICEF | 0 | 14285.7143 | March-Dec | Masiko /Lubwama | Eva | Done during support supervision | [12 empty] | 1 | 1 | 1 | 1
Vaccine, Logistics, Equipments and Infrastructure | Strengthen district and Facility levele cold chain and vaccine management practices | Conduct preventive maintenance for cold chain equipment in 116 districts | Maintenance plan/Report | Funded | High | UNICEF | 0 | 22900 | MAR, APR | Cold chain team | Eva | Prior to Rota vaccine introduction | [12 empty] | 1 | 1 | 0 | 0
Vaccine, Logistics, Equipments and Infrastructure | Strengthen district and Facility levele cold chain and vaccine management practices | Establish and train 14 regional cold chain maintenance teams | Training plan/programme/report | Funded | High | UNICEF/PATH | 0 | 75680 | APR, MAY | Lubwama/Masiko | Eva/Brian | [13 empty] | 0 | 1 | 0 | 0
Vaccine, Logistics, Equipments and Infrastructure | Strengthen district and Facility levele cold chain and vaccine management practices | Conduct quarterly support supervision to strengthen temperature montioring review and reporting at DVS | Supervision plan/Reports | Funded | Medium | UNICEF | 0 | 14285.7143 | MAR, JUN, SEPT, DEC | Masiko /Lubwama | Eva | Done during support supervision | [12 empty] | 1 | 1 | 1 | 1
Vaccine, Logistics, Equipments and Infrastructure | Strengthen district and Facility levele cold chain and vaccine management practices | Develop a tool for collection and analysis of the temperature monitoring data from vaccine storage facilities-TA | Finalised Temperature data collection and analysisi tool | Funded | Medium | PATH | 0 | 21000 | MAY | Lubwama/Lanyero | Brian | TA Required | [12 empty] | 0 | 1 | 0 | 0
Vaccine, Logistics, Equipments and Infrastructure | Strengthen district and Facility levele cold chain and vaccine management practices | Compile monthly updates on daily temperature charting for the CVS to be shared in the Vaccine Management TWG meeting | Monthly report shared |  | High | NMS | 0 |  | Jan-Dec | William Musubire |  | William to share and review during the logistics working group meeting | [12 empty] | 1 | 1 | 1 | 1
Vaccine, Logistics, Equipments and Infrastructure | Strengthen district and Facility levele cold chain and vaccine management practices | Develop ToRs for national immunization supply chain & logistics (iSCL) working group | Availability of iSCLWG TOR |  | High | UNICEF/PATH | 0 | 45000 | FEB, MAR | Pamela Zaninka | Eva/Brian | [13 empty] | 1 | 0 | 0 | 0
Vaccine, Logistics, Equipments and Infrastructure | Strengthen district and Facility levele cold chain and vaccine management practices | Conduct monthly iSCL working group meetings | Minutes |  | High | UNICEF/PATH | 0 | 2000 | JAN-DEC | Zaninka/Kiwanuka | Eva/Brian | [13 empty] | 1 | 1 | 1 | 1
Vaccine, Logistics, Equipments and Infrastructure | Strengthen district and Facility levele cold chain and vaccine management practices | Design, install and implemet an LMIS system for country immunisation supply chain management | Consultancy report |  | Medium | UNICEF | 0 | 31000 | June | Zaninka/Musubire | Eva | [13 empty] | 0 | 1 | 0 | 0
Vaccine, Logistics, Equipments and Infrastructure | Strengthen district and Facility levele cold chain and vaccine management practices | Conduct EVM self assessment in selected dsitricts and recognise best performers as a means to strengthen immunisation supply chain and key EVM priority areas | EVMA Plan/Report |  | High | UNICEF/PATH | 0 | 79300 | AUG, SEPT | Zaninka/Musubire | Eva | [13 empty] | 0 | 0 | 1 | 0
Vaccine, Logistics, Equipments and Infrastructure | Strengthen district and Facility levele cold chain and vaccine management practices | Update cold chain inventory bi-annually | Inventory report | Funded | High | UNICEF | 0 | 1500 | JUN, DEC | Masiko/Lubwama/Lanyero | Eva | [13 empty] | 0 | 1 | 0 | 1
Vaccine, Logistics, Equipments and Infrastructure | Strengthen district and Facility levele cold chain and vaccine management practices | Roll out the updated 2017 district monthly vaccine order form and the web-based version to all districts | Vaccine order form in the districts/Roll out Report |  | Medium | CHAI | 0 | 1000 | MAR, JUN | William Musubire | Lorraine | [13 empty] | 0 | 1 | 0 | 0
Vaccine, Logistics, Equipments and Infrastructure | Strengthen district and Facility levele cold chain and vaccine management practices | Cold chain and logistics management activities for polio SIAs and Rota introduction | Logistics plan/Report |  | High | WHO | 0 |  | FEB, MAR, APR | Zaninka/Musubire | Annet | [13 empty] | 1 | 1 | 0 | 0
Vaccine, Logistics, Equipments and Infrastructure | Strengthen district and Facility levele cold chain and vaccine management practices | Development of deployment plan for the HSS2/CCEOP equipment | Deployment plan | Funded | High | UNICEF | 0 | 1500 | MAY, JUN | Lubwama/Masiko/Lanyero | Eva | [13 empty] | 0 | 1 | 0 | 0
Vaccine, Logistics, Equipments and Infrastructure | Strengthen district and Facility levele cold chain and vaccine management practices | Conduct cold chain technical capacity enhancement program for DCCA/T. | Concept note/mentorship plan/report |  | Medium | GoU/PATH | 0 | 5200 | MAY-DEC | Lubwama/Masiko/Lanyero |  | To work with KCCA to have model facilities for mentorship | [12 empty] | 0 | 1 | 1 | 1
Disease Surveillance | Provide strategic direction and planning for VPD surveillance system | Conduct a desk review of the current VPD surveillance system | Technical reports | Funded | High | WHO | 0 | 2000 | June | Ampaire | Katushabe | AFRO, IST, HQ with locals | [12 empty] | 0 | 1 | 0 | 0
Disease Surveillance | Increase knowledge of surveillance practices among hospital and facility staff | Conduct six regional workshops for health facility surveillance FPs on VPD surveillance | Training schedule & Report | Funded | High | CDC/AFENET/WHO | 0 | 76000 | FEB, MAR | Ampeire | Mwanje/Patricia | Trainings in 7 regions | [12 empty] | 1 | 0 | 0 | 0
Disease Surveillance | Increase case detection rate of VPDs within IDSR framework | Deploy STOP teams in low performing districts (national and international) | Technical reports | Funded | High | WHO/CDC | 0 | 76080 | FEB-DEC | Ampeire/Seguya | Katushabe | [13 empty] | 1 | 1 | 1 | 1
Disease Surveillance | Ensure quality performance indicators of new vaccine sentinel sites are attained and sustained | Conduct regular review meetings and support supervision visits | Technical reports | Funded | High | WHO | 0 | 45664 | FEB-DEC | Ampeire | Annet | five sentinel sites | [12 empty] | 1 | 1 | 1 | 1
Disease Surveillance | Ensure availability of surveillance reporting tools | Print and distribute the VPD case based booklet | Availability of VPD booklet at the HF level in the 10 new districts | Funded | Medium | CDC/AFENET | 0 | 8000 | FEB, MAR | Ampeire | Mwanje/Patricia | 10 new districts | [12 empty] | 1 | 0 | 0 | 0
Disease Surveillance | Ensure availability of surveillance job aiides at the health facility level | Review, print and distribute surveillance job aides to all districts | Availability of Job aids at the health facility level | Funded | High | CDC/AFENET | 0 | 68000 | FEB, MAR | Ampeire | Mwanje/Patricia | Pending endorsement from UNEPI | [12 empty] | 1 | 0 | 0 | 0
Disease Surveillance | Strengthen the district and regional referral hospital AEFI surveillance system | Establish a sentinel AEFI surveillance system at the regional referral shospitals | Technical reports | Funded | High | WHO | 0 | 42000 | FEB-DEC | Ampeire/NDA | Annet | All districts will be reached during Rota trainings but focus at RRRHs | [12 empty] | 1 | 1 | 1 | 1
Disease Surveillance | Improve the quality and regularity of active surveillance visits at district level | National and EPI/IDSR regional supervision visits at the district and selected heakkth facilities | VPD surveillance performance indicattors | Funded | High | WHO | 0 | 194000 | Jan - Dec | Ampeire | Andrew | establish additional region, strengthen existing | [12 empty] | 1 | 1 | 1 | 1
Disease Surveillance | Ensure full accredidation of measles and polio laboratory | Provide supplies to EPI laboratory | measles and polio accredidation report | Funded | Medium | WHO/CDC/AFENET | 0 | 100036 | JAN, FEB, MAR | Ampeire | Annet/Mwanje/Patricia | TSAs provided | [12 empty] | 1 | 1 | 1 | 1
Disease Surveillance | Ensure timely investigation and response to suspected and confirmed VPD outbreaks | Build capacity at national and district level within the IDSR framework | Timely outbreak investigation reports | Funded | High | CDC/AFENET/WHO | 0 | 198000 | FEB-DEC | Ampeire | Mwanje/Patricia/Katushabe | Reports should be available within 72 hours | [12 empty] | 1 | 1 | 1 | 1
Disease Surveillance | Supplement AFP surveillance with environmental surveillance | Establish environmental surveillance system in Uganda | Monthly laboratory reports | Funded | High | WHO | 0 | 40000 | MAY-DEC | Ampeire | Annet | [13 empty] | 0 | 1 | 1 | 1
Disease Surveillance | Improve the performance of quality surveillance indicators in all districts | Conduct national and regional surveillance review meetings | Technical reports | Funded | High | WHO | 0 | 135000 | FEB-DEC | Ampeire/Seguya | Katushabe | 2 national and 14 regional meetings | [12 empty] | 1 | 1 | 1 | 1
Polio endgame | Stainability of the EPI polio transition plan | Provide Technical support for the implementation of polio transition plan | Implementation plan | Funded | High | WHO | 0 | 6417 | May - Dec | Ampeire | Opar | Polio transition plan | [12 empty] | 0 | 1 | 1 | 1
Polio endgame | Maintain polio free country | Conduct preventative Polio SIAs in high risk districts | Report | Funded | High | WHO/UNICEF | 0 | 2821747 | APR | Luzze | Annet/Eva | 67% of <5Y | [12 empty] | 0 | 1 | 0 | 0
Polio endgame | Timely detection, confirmation, reporting and response to VPD outbreaks | Conduct Polio SIAs in high risk districts on Uganda | Report | Funded | High | WHO | 0 | 2821747 | APR | Ampeire/Seguya | Katushabe | [13 empty] | 1 | 1 | 1 | 1
Note on C2: Atuhaire Brian: UNICEF has funding for establishment of the immunization fund which PATH is also working on. It is different from this activity. I suggest considering it as a separate activity Patrick Banura Brian which are those 2 separate activities so that we outline them properly? Have changed the activity to UNICEF/PATH. Provide the funds for that activity of PATH
Note on G20: Banura Patrick: UNICEF/PATH/CHAI=10000+7490+1000 respectively
Note on G21: Banura Patrick: UNICEF/PATH/CHAI=10000+1875.5+1000 respectively
Note on G52: Banura Patrick: MCSP-SS4RI printing $5,500
Note on G57: Banura Patrick: MCSP-SS4RI : OPL training 12 districts $60,300
Note on G58: Banura Patrick: WHO to confirm
Note on G92: Banura Patrick: UNICEF +PATH = 57300+22000 respectively
Note on M99: Banura Patrick: Funds Expire in April 2017. UNEPI to give guidance on the regions and districts